## Slide 1
Conceptual Design Overview & Key Findings
Anexinet ISG Delivery Team

## Slide 2
Microsoft/Exchange/SQL
Citrix/EUC
Physical Network
Core Redesign Overview
vSphere Upgrade/C7000 Redesign
vSphere Cluster Consolidation
vSphere Licensing
P2V
Storage
vSphere Networking Design
Backup
Disaster Recovery
February Test Overview
Next Steps
AGENDA

## Slide 3
Key Findings

## Slide 4
Windows 2003 Server Upgrades (End-of-Life)
AD Upgrade & Cleanup Initiative
  AD Forest and Domain Functionality from 2003 to Current
  Stale Group and User Cleanup
    i.e.: 4100 Groups in AD
  Decommission 2003 Domain Controllers
    Pre-requisite: RightFax Upgrade (In Progress)
Exchange 2003/2007 Upgrade
  Pre-requisite: RightFax Upgrade (In Progress)
  Implement Redundancy/Resiliency Measures
SQL Migration and Consolidation
  Pre-requisite: Data Warehouse Architect (In Progress)
Full Design Deliverable (In Progress)
Microsoft/Exchange/SQL

## Slide 5
Microsoft Forest Overview

## Slide 6
Citrix Hotfix/Version Inconsistencies (4.5, 6.5, & 5.6 Environments)
  Citrix Environment Consolidation to Version 7.6 of XenDesktop
  Implement Citrix Leading Practices Throughout
  NetScaler Configuration and Optimizations
  Monitoring Design Initiative (part of full detailed design)
    eG Innovations Overview
Single Image Management via Provisioning Services
  XenApp and XenDesktop Groups
  More Centralized Management of Data
Server and Storage Optimizations
  PernixData Overview (Next Steps)
Endpoint Device Recap Potential
  Update Thin Clients in the Field – Windows Embedded
Onboarding and User Pilot Testing for Eventual New Environment Build
  150-200 Users/Week
Citrix

## Slide 7
Base image 1
XenApp Published Applications
Base image 2
XenApp Hosted Shared Desktop
Base image 3
XenClient (Optional)
Base image 4
XenDesktop Pooled Desktops
Base image 5
PCs managed by SCCM
Application Assessment Method/Approach
Phased application assessment
Recommended Citrix/App Delivery Model

## Slide 8
Replace 5020s, 6509s, C2960s, and FWs
  Cisco Nexus – VPC technology
  Cisco ASA 55X5 Series with Firepower capabilities
  Cisco ISR series routers
Preserve overall Layer2 design
  Possible additions
Possible use of WAN compression
  Will wait to see the impact of vSphere Replication on WAN and FW
WAN uses:
  vSphere Replication
  Exchange DAG replication
  SQL DAG replication?
  Physiotherapy remote facilities (core business)
  Backup replication
Physical Network

## Slide 10
Upgrade three c7000 chassis’
Unlink c7000 chassis
Consolidate vSphere hosts to blades
Standardize all vSphere to 5.5 U2
Standardize all SAN to VNX 7500 via FC
Core Redesign overview

## Slide 11
Upgrade 24 Cluster1 vSphere hosts to 5.5
Install/configure HP OneView
New c7000 design:
  Latest HP firmware
  Use non-stacked networking
  Connect to new external FC switches
  Connect to DMZ VLAN
Add 8 new vSphere 5.5 hosts to Cluster1
Migrate VMs to new c7000 and upgrade existing chassis’
Redistribute VMs amongst c7000 chassis’
Upgrade VM tools and vHW
vSphere Upgrade/c7000 Redesign

## Slide 12
Add DMZ VLAN to Cluster1 hosts
Migrate all Cluster3/DMZ VMs (23) to Cluster1
Reuse DMZ host in Management Cluster (Cluster2)
Migrate Cluster2 SAN type to FC
Upgrade Cluster2 to vSphere 5.5
Vsphere Cluster Consolidation

## Slide 13
Upgrade vSphere licensing to 5.5 Enterprise Plus
Will require purchasing vSphere 5 Enterprise licensing to Enterprise Plus
Will provide licensing for 32 current blades + 3 DL360s, with headroom for 14 additional hosts
Vsphere Licensing

## Slide 14
Benefits of P2V:
  Reduces dedicated LUNs that can be added to vSphere pools and shared among all vSphere hosts
  VMs can be replicated to Hosting.com DR site
  Reduction of footprint at SunGard and Hosting.com
  Consolidation of resources to three c7000 chassis’
  Reduced support costs as rack servers are retired
Goal: P2V as many physical servers as possible
  Virtualizing physical servers frees up Rackspace at SunGard and enables DR via SRM to Hosting.com
Note P2V exceptions like:
  Exchange
  NextGenDB
  Extremely large memory servers
List Required capacity for new VMs
Table showing before and after P2V
P2v

## Slide 15
Will Exchange Storage stay SAN based?
EMC Disk Pools:
  Current have 3 vSphere pools: High, Mid, Low
  Looking at possibility of moving to 2 pools(Gold / Bronze)
P2V’s will free up LUNs that can be recreated and added to vSphere pools
  Space will be recovered from the P2V process. Used LUNs will be returned to the same disk pool.
2TB LUNs with Datastore Clusters aligned with Storage pools
  Have a couple of large VMDKs (1.7 TB). Considering changing to 3TB LUNs to reduce LUNs as well as increase size for large VMDKs
Powerpath is installed on most physical servers with various versions
  Either unlicensed of licensed for Powerpath migration enabler
Storage

## Slide 16: vSphere Networking Cluster1 Blades
Any changes to VLANs?
OA is on 172.26.15.0/24

## Slide 17: Backup
Current issues:
  VADP backups failing and leaving VM snapshots behind
  Backup of DB VMs are failing to quiesce
  No offsite archiving solution
  License capacity calculation issue: will be fixed with Service Pack 11
Commvault Simpana
Simpana physical server with FC HBA (add)
VADP based backups from physical Simpana server(s)
Backup destination: 3PAR via FC (currently iSCSI)
  Used to leverage HP StorServer NAS servers as a backup measure
Notes: 44 existing blades
2 of which are older AMD CPU

## Slide 18: Backup
Possibly could use Commvault to replicate backup jobs to HP ServStore servers at Hosting.com?
Recommend leveraging 3PAR at HOSTING.COM
  Replicate backup data with 3PAR’s remote copy technology
  Metadata will be replicated with SQL mirroring to a physical Commvault server at HOSTING.COM
  Same server will be used for replicating the NAS data
Notes: 44 existing blades
2 of which are older AMD CPU

## Slide 19: Disaster Recovery - WAN
SunGard WAN summary 5/18-6/10
Peak usage – 116Mbps of current 250Mbps
Notes: 44 existing blades
2 of which are older AMD CPU

## Slide 20: Disaster Recovery - VMs
vSphere Replication 5.8 (no special LUN grouping required)
SAN replication is not in scope
vSphere Site Recovery Manager 5.8 (fully managed by Hosting.com)
WAN: Currently 250Mb (can burst higher)
WAN: Current FWs are maxing out on CPU
VMs to be replicated:
  Approximately 300
  DR Hosting contract estimated based on 300 VMs in Cluster1
Notes: 44 existing blades
2 of which are older AMD CPU

## Slide 21: Disaster Recovery-Physical Servers
SQL – Will native SQL replication be configured?
Need to identify all physical servers (post P2V) that need to be replicated
There are contractual limitations at Hosting.com on physical servers
Physical servers freed by P2V could be moved to Hosting.com as standby hosts for physical server recovery
Physical servers that have built-in replication (like Exchange) could be replicated from physical (protected site) to VM (recovery)
Physical appliances? (Barracuda, Mail archive, etc.?)
  Are there virtual instances that can be run in DR site?
  How long can Physio VMs run in DR failover mode?
Notes: 44 existing blades
2 of which are older AMD CPU

## Slide 22
Next Steps

## Slide 23
Short Term
  Full Detailed Design Completion (In Progress)
    Delivery date – June 26th (Every practice area – posted to Teamwork)
  Client Design Review – Physiotherapy
  Phased Approach List for Implementation - Anexinet
  Continue Migration Efforts and Testing
  Implement Initial Configuration
Long Term
  Finalize Implementation and Remediation Effort
  DR Environment and Considerations
Next Steps

## Slide 24: Planned Implementation Roadmap

## Slide 25
Next Steps/Microsoft Residency Work Stream
Issue | Priority | Notes | Workstream | Complete
RightFax Upgrade | High | RightFax upgrade is required to decommission the Exchange 2003 servers from the Org. It also utilizes the Windows 2003 Domain Controllers | MS Residency | Needed prior to AD work
Active Directory NTP Time | Med | NTP is not configured correctly in the Domain Controllers | MS Residency | 
Empty Group Clean up | Low | Approximately 4,100 Empty Groups in AD | MS Residency | 
DC Operating System Patches | Med | DCs are missing Patches or nto configured to receive patches from MS Update | MS Residency | 
Exchange Service Packs | High | Legacy Exchange servers are not at the required service pack level for co-existence with Exchange 2013 | MS Residency | 
AD Account Cleanup | Low | Review and remediate AD User and Computer accounts | MS Residency | 
Licensing Server Installation | High | Install and Configure KMS Server for the Domain | MS Residency | 
MS Assesment and Planning Toolkit | High | Install and Configure MAP Toolkit for Licensing assessments and reports | MS Residency | 
Service Account Review | Med | Review Service Accounts used on all windows servers. Convert to Group Managed Service Accounts | MS Residency | 
Scheduled Tasks Review | Med | Scheduled Tasks are scattered about on servers with little to no documentation. Document all AT tasks and convert to gMSA where applicable. Review Possible Consilidation and task relocation. | MS Residency | 
Server Rights Review | Low | Review Local User Rights on all Windows servers. Implement Role Based access where applicable. | MS Residency | 
Application Review | Med | Document all Server based aaplication in the PhysioCorp domain. Identify all apps/app owners/business units and document any/all support contracts | MS Residency | 
Shavlik Review | Med | Review current Shavlik installation for possibility of leveraging system to patch non-domain joined computers at remote sites | MS Residency | 
Server Update Process | Med | Develop and Document Patching automatic patching process for all Servers | MS Residency | 
Solar Winds Monitoring Review | Low | Review monitoring of servers and application by Solar Winds | MS Residency | 
Laptop Images for Remote Sites | Med | Work with Physio staff to augment laptop image configuration and deployment. | MS Residency | 
AD Rights and Delegation | Low | Develop Strategy for Role Based Access for AD Administrative rights | MS Residency | 

## Slide 26
Questions?